Manual on Standard Operating Procedures (SOP’s) and Critical Control Points for Trial establishments

Objective field trial

-To meet specific breeding targets such as high yield, starch content, high dry matter, increased carotenoid content, disease and pest resistance, mealiness, agronomy packages

Needful activities

-  Field acquisition, field tillage operations, field layout, planting, field maintenance and agronomy practices, data collection and evaluation

Materials needed

- Tablet or mobile phones for data capture using fieldbook, stick pegs, barcode labels, sisal twines, markers

Standard Operating Procedures and Critical Control Points for setting up field trials

| s/n | Standard Operating Procedures | Critical Control Points |
| --- | --- | --- |
| 1 | State objectives of trial clearly | Purpose for the trial must be known to team members |
| 2 | Provide list of genotypes to be evaluated and the corresponding checks | selection of genotypes made as soon as data is analysed |
| 3 | Availability of land | Ensure timely request for land |
| 4 | Availability of planting materials. | Ensure sufficient materials for the selected genotypes |
| 5 | Specify the experimental design, number of replicates and blocks | strictly adhere to laid out design |
| 6 | Specify the plot size and planting spaces | strictly adhere to specification for plot size and spacing |
| 7 | Determine if the trial is to be set up in single or multi-location | Team workers must be informed the number of locations for the various trials |
| 8 | Outline important activities for trial setup | Ensure adequate availability of materials for setting up trials |
| 9 | Design the layout file using cassavabase | Ensure you are using proper design, and naming convention for plots |
| 10 | Generate the field book file and trait file from cassava base and load in the electronic device |  |
| 11 | Preparation of planting materials, properly packed in a polythene bags and labeled (each polythene bag contains only one genotype) | Ensure making cutting from good stem parts with at least 3-5 nodes |
| 12 | Mark out the field block by block and put the stick pegs accordingly | Availability of enough stick pegs for marking |
| 13 | Check all the pegging against randomization to ensure it is properly done | Field experts must ensure pegging are in their corresponding randomization |
| 14 | Ensure careful transportation of the planting materials to the field and kept under shade before the day of planting not later than 72 hrs. after cutting | Availability of enough vehicles and skillful personnel to convey planting materials to the field |
| 15 | Research supervisor must be available during the time of planting | Effective communication with research supervisor before planting |
| 16 | Lay and plant the materials using layout file | Materials for cassava cuttings must be available |
| 17 | Determine the orientation and depth of planting suitable to your objective but usually slant orientation (46-60o) and about 10 cm planting depth is used | Ensure that a qualified technician does the planting to required measurement |
| 18 | Assign responsibilities with team members | Effective interaction with team members to meet target |
| 19 | Spray pre-emergence herbicide latest 24 hrs after planting | Ensure the various chemicals and, spraying materials needed for spraying after planting is available and skillful personnel to handle the spraying at the set time |
| 20 | Generate Barcode labels from cassavabase and tag them to each plant/plot in the field | Ensure the availability of labels |
| 21 | Put sign board to indicate information on the trial | Sign board must display appropriate trial information |
| 22 | Put fire break surrounding the trials during dry season | Make about 5m fire break |